## Plan
Start Date | End Date | Task/Deliverable | Owner | Status
Writing and Editing
| 2015-06-15 | Executive Summary: Written and Locked | Joe, Shpat, Susan
2015-06-16 | 2015-06-17 | Executive Summary: Copyediting | Copywriter
| 2015-06-16 | Part I (First 3 chapters) Written and Locked | Joe, team
2015-06-18 | 2015-06-22 | Part I (First 3 chapters) Copyediting | Copywriter
JUNE
| 2015-06-18 | Conclusion: Written and Locked | Joe, Susan |  | MON | TUE | WED | THU | FRI
2015-06-22 | 2015-06-24 | Conclusion: Copyediting | Copywriter |  | 8 | 9 | 10 | 11 | 12
| 2015-06-22 | Technical chapters: Written and Locked | Joe, team |  | 15 | 16 | 17 | 18 | 19
2015-06-24 | 2015-06-29 | Technical chapters: Copyediting (light) | Copywriter
[5 empty] | 22 | 23 | 24 | 25 | 26
Graphics
2015-06-11 | 2015-06-12 | List and descriptions finalized and sent to Designer | Shpat |  | 29 | 30 | 1 | 2 | 3
| 2015-06-22 | First pass at graphics done | Designer, Shpat
2015-06-22 | 2015-06-26 | Fine tuning, if any, to fit the layout | Designer, Shpat
[5 empty] | 6 | 7 | 8 | 9 | 10
Layout
2015-06-12 | 2015-06-17 | Draft template | Shpat
2015-06-18 | 2015-06-19 | Example placement of Executive Summary | Shpat
| 2015-06-26 | Layout finalized | Shpat
Deliverables
| 2015-06-29 | Milestone - Initial deliverables due to Susan | Galois
Report content is complete
Executive Summary is complete (PDF)
Background is complete (PDF)
Illustrations are complete and integrated (PDF)
2015-06-30 | 2015-07-02 | Out for final review: minor corrections accepted
| 2015-07-03 | Executive summary goes to print | Galois
2015-07-06 | 2015-07-08 | Presentation preparation | JoeK, ShpatM

## old
Start Date | End Date | Task/Deliverable | Owner | Status
2015-06-08 |  | Project Planning Discussion | Galois | Done
2015-06-08 | 2015-06-10 | Executive Summary: Draft | JoeK, ShpatM | Ongoing
2015-06-09 | 2015-06-12 | RSE Content: Write | DanZ
2015-06-09 | 2015-06-12 | Crypto Content: Write | JoeK
2015-06-10 | TBD | Graphics: Develop | Graphics Artist
2015-06-11 | TBD | Background & Executive Summary: Edit | Copy Editor
2015-06-11 | TBD | LaTex to InDesign Conversion | ShpatM
2015-06-15 | 2015-06-19 | Feasibility Chapter: Write | JoeK
| 2015-06-25 | Milestone - Repository Locked | Galois
| 2015-06-29 | Milestone - Initial deliverables due to Susan | Galois
Report content is complete
Executive Summary is complete (PDF)
Background is complete (PDF)
Illustrations are complete and integrated (PDF)
Copy editing remains to be completed
| 2015-06-29 | Milestone - Website Staged | Susan
| 2015-07-03 | Milestone - Executive Summary Printed | Galois
| 2015-07-09 | Milestone - Final deliverables due to Susan | Galois
| 2015-07-11 | Milestone - Website and Repository go live | Susan