## Plan 1.0
Start Date | End Date | Task/Deliverable | Owner | Status
2015-06-08 |  | Project Planning Discussion | Galois | Done
2015-06-08 | 2015-06-10 | Executive Summary: Draft | JoeK, ShpatM | Ongoing
2015-06-09 | 2015-06-12 | RSE Content: Write | DanZ
2015-06-09 | 2015-06-12 | Crypto Content: Write | JoeK
2015-06-10 | TBD | Graphics: Develop | Graphics Artist
2015-06-11 | TBD | Background & Executive Summary: Edit | Copy Editor
2015-06-11 | TBD | LaTex to InDesign Conversion | ShpatM
2015-06-15 | 2015-06-19 | Feasibility Chapter: Write | JoeK
| 2015-06-25 | Milestone - Repository Locked | Galois
| 2015-06-29 | Milestone - Initial deliverables due to Susan | Galois
Report content is complete
Executive Summary is complete (PDF)
Background is complete (PDF)
Illustrations are complete and integrated (PDF)
Copy editing remains to be completed
| 2015-06-29 | Milestone - Website Staged | Susan
| 2015-07-03 | Milestone - Executive Summary Printed | Galois
| 2015-07-09 | Milestone - Final deliverables due to Susan | Galois
| 2015-07-11 | Milestone - Website and Repository go live | Susan