## Current Plan 2015-16
End-to-End Verifiable Internet Voting
Planning to Completion
Updated: March 26, 2015 |  | Assigned | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July
|  |  | 3/1-7 | 3/8-14 | 3/15-21 | 3/22-28 | 3/29-4/4 | 4/5-11 | 4/12-18 | 4/19-25 | 4/26-5/2 | 5/3-9 | 5/10-16 | 5/17-23 | 5/24-30 | 5/31-6/6 | 6/7-13 | 6/14-20 | 6/21-27 | 6/28-7/4 | 7/5-11 | 7/12-18 | 7/19-25
|  |  | Week 1 | Week2 | Week 3 | Week 4 | Week 1 | Week2 | Week 3 | Week 4 | Week 5 | Week 1 | Week2 | Week 3 | Week 4 | Week 1 | Week2 | Week 3 | Week 4 | Week 1 | Week2 | Week 3 | Week 4
REPORT WRITING
Detailed Report Outline | bar: Week 1 to Week2
100%
WRITING AND EDITING - Body Narrative
Chapters 3-5 | bar: Week2 to Week2
| Chapter: Remote Voting | Philip | Week 4: 30%; Week 1: 45%; Week2: 70%; Week 3: 95%; Week 4: 100%
| Chapter: E2E VIV Explained | Daniel / Philip / Adam | Week 4: 25%; Week 1: 45%; Week2: 75%; Week 3: 95%; Week 4: 100%
| Chapter: Required Properties of E2E VIV Systems | Dan | Week 4: 60%; Week 1: 100%; Week2: 100%; Week 3: 100%; Week 4: 100%
WRITING AND EDITING - Technical Sections
Chapters 6-9 | bar: Week 4 to Week 4
| Chapter: Crypto Specification | Dan / Joe | Week 4: 15%; Week 1: 15%; Week2: 15%; Week 3: 15%; Week 4: 15%
| Chapter: Architecture | Dan / Joe | Week 4: 15%; Week 1: 15%; Week2: 25%; Week 3: 30%; Week 4: 40%
| Chapter: System Specification | Dan / Joe | Week 4: 15%; Week 1: 15%; Week2: 25%; Week 3: 25%; Week 4: 25%
| Chapter: Verification and Validation | Dan / Joe / Adam | Week 4: 20%; Week 1: 20%; Week2: 25%; Week 3: 25%; Week 4: 40%
WRITING AND EDITING - Additional Sections
Remaining Chapters | bar: Week 3 to Week2
| Chapter: Executive Summary | Joe / Susan | bar: Week 4 to Week 4
| Chapter: Introduction | Joe / Susan | Week 4: 25%; Week 1: 25%; Week2: 70%; Week 3: 85%; Week 4: 90%
| Chapter: Feasibility | ? | Week 4: 25%; Week 1: 25%; Week2: 25%; Week 3: 25%; Week 4: 25%
| Chapter: Conclusion | Joe / Susan | bar: Week 4 to Week 4
| Chapter: Appendices | Various | Week 4: ?; Week 1: ?; Week2: ?; Week 3: ?; Week 4: 25%
CIRCULATE ROUGH DRAFT
Expert Feedback
Set Dates for Section Releases | bar: Week2
Announce to Experts | bar: Week 3
Distribute Report for Review and Feedback | bar: Week 4 to Week 5
Incorporate Feedback | bar: Week 1 to Week2
UX STUDY AND TESTING
Usability Design and Analysis
| Study Design |  | Week 3: 85%; Week 4: 90%
Implementation | bar: Week2 to Week 5
Execution | bar: Week 3 to Week 1
Analysis | bar: Week 3; Week 1 to Week2
Incorporate into Draft and Review | bar: Week 3; Week2 to Week 3
ROADSHOW
Meet with LEO and Stakeholder Groups | bar: Week 4
Wed 27 May – DC - North East Region meeting | bar: Week 4
Thu 28 May – FL - Southern Region meeting | bar: Week 4
Fri 29 May – WA State – North Western Region meeting | bar: Week 4
Weekend Sat/Sun May 30/31– you are home in Portland | bar: Week 1
Mon Jun 1 – Portland/Galois – meetings with management and team | bar: Week 1
Tue Jun 2 - TX meeting | bar: Week 1
Wed Jun 3 – NM for Western Region meeting (CO could join this or TX) | bar: Week 1
Thu Jun 4 – Present at NCSL | bar: Week 1
RELEASE FINAL REPORT
Final round of edits and Review | bar: Week2 to Week 4
Final Release of Report - July - Present at NASS in Maine | bar: Week2

## Sheet1
MVA goes mobile and gets religion